## Team
Initials | First | Last | Email | GitHub Username
ak | Avaneesh | Kolluri | akolluri@stevens.edu | AvaneeshKolluri
el | Erick | Lim | elim1@stevens.edu | RedRoach51
pp | Pratim | Patel | ppate78@stevens.edu | PratimPatel99
su | Srikanth | Uppada | suppada@stevens.edu | sriksrik7
zg | Zachary | George | zgeorge@stevens.edu | ztylergeorge
|  |  | GitHub Repository: | https://github.com/AvaneeshKolluri/Agile_Methods_Project

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US01 | Dates before current date | ak | Done
1 | US02 | Birth before marriage | ak | Done | Status stages : Assigned, InProgress, Done
1 | US03 | Birth before death | el | Done
1 | US04 | Marriage before divorce | el | Done
1 | US05 | Marriage before death | pp | Done
1 | US06 | Divorce before death | pp | Done
1 | US07 | Less then 150 years old | su | Done
1 | US08 | Birth before marriage of parents | su | Done
1 | US09 | Birth before death of parents | zg | Done
1 | US10 | Marriage after 14 | zg | Done
2 | US11 | No bigamy | ak | Assigned
2 | US12 | Parents not too old | ak | Assigned
2 | US13 | Siblings spacing | el | Assigned
2 | US14 | Multiple births <= 5 | el | Assigned
2 | US15 | Fewer than 15 siblings | pp | Assigned
2 | US16 | Male last names | pp | Assigned
2 | US17 | No marriages to descendants | su | Assigned
2 | US18 | Siblings should not marry | su | Assigned
2 | US19 | First cousins should not marry | zg | Assigned
2 | US20 | Aunts and uncles | zg | Assigned
3 | US21 | Correct gender for role | ak | Assigned
3 | US22 | Unique IDs | ak | Assigned
3 | US23 | Unique name and birth date | el | Assigned
3 | US24 | Unique families by spouses | el | Assigned
3 | US25 | Unique first names in families | pp | Assigned
3 | US26 | Corresponding entries | pp | Assigned
3 | US27 | Include individual ages | su | Assigned
3 | US28 | Order siblings by age | su | Assigned
3 | US29 | List deceased | zg | Assigned
3 | US30 | List living married | zg | Assigned
4 | US31 | List living single | ak | Assigned
4 | US32 | List multiple births | ak | Assigned
4 | US33 | List orphans | el | Assigned
4 | US34 | List large age differences | el | Assigned
4 | US35 | List recent births | pp | Assigned
4 | US36 | List recent deaths | pp | Assigned
4 | US37 | List recent survivors | su | Assigned
4 | US38 | List upcoming birthdays | su | Assigned
4 | US39 | List upcoming anniversaries | zg | Assigned
4 | US40 | Include input line numbers | zg | Assigned

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2020-09-20 | 40 |  | 0
Sprint 1 | 2020-10-05 | 10 | 0 | 0 | 120 | 0
Sprint 2 | 2020-10-19 | 10 | 0 | 0 | 135 | 0
Sprint 3 | 2020-11-02 | 10 | 0 | 0 | 160 | 0
Sprint 4 | 2020-11-16 | 10 | 0 | 0 | 145 | 0
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2020-09-20 | 40 | 0 | 0 | 0 | 0
2020-10-05 | 30 | 10 | 399 | 690 | 34.6957
2020-10-26 | 20 | 10 | 330 | 600 | -6.9
2020-11-09
2020-11-16

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Dates before current date | ak | Assigned | 3 | 60 | 42 | 60 | Completed
T01.01 | Store current date | ak | Assigned |  |  |  |  | Task finished
T01.02 | Store date field | ak | Assigned |  |  |  |  | Task finished
T01.03 | Compare to date field | ak | Assigned |  |  |  |  | Task finished
US02 | Birth before marriage | ak | Assigned | 5 | 100 | 45 | 90 | Completed
T02.01 | Check if there was a marriage | ak | Assigned |  |  |  |  | Task finished
T02.02 | Store birth date | ak | Assigned |  |  |  |  | Task finished
T02.03 | Store marriage date | ak | Assigned |  |  |  |  | Task finished
T02.04 | Compare birth date and marriage date | ak | Assigned |  |  |  |  | Task finished
US03 | Birth before death | el | Assigned | 5 | 100 | 45 | 120 | Completed
T03.01 | Check if there was a death | el | Assigned |  |  |  |  | Task finished
T03.02 | Store birth date | el | Assigned |  |  |  |  | Task finished
T03.03 | Store death date | el | Assigned |  |  |  |  | Task finished
T03.04 | Compare birth date and death date | el | Assigned |  |  |  |  | Task finished
US04 | Marriage before divorce | el | Assigned | 7 | 140 | 45 | 45 | Completed
T04.01 | Check if there was a marriage | el | Assigned |  |  |  |  | Task finished
T04.02 | Check if there was a divorce | el | Assigned |  |  |  |  | Task finished
T04.03 | Store marriage date | el | Assigned |  |  |  |  | Task finished
T04.04 | Store divorce date | el | Assigned |  |  |  |  | Task finished
T04.05 | Compare marriage date and divorce date | el | Assigned |  |  |  |  | Task finished
US05 | Marriage before death | pp | Assigned | 7 | 140 | 40 | 55 | Completed
T05.01 | Check if there was a marriage | pp | Assigned |  |  |  |  | Task finished
T05.02 | Check if there was a death | pp | Assigned |  |  |  |  | Task finished
T05.03 | Store marriage date | pp | Assigned |  |  |  |  | Task finished
T05.04 | Store death date | pp | Assigned |  |  |  |  | Task finished
T05.05 | Compare marriage date and death date | pp | Assigned |  |  |  |  | Task finished
US06 | Divorce before death | pp | Assigned | 7 | 140 | 40 | 65 | Completed
T06.01 | Check if there was a divorce | pp | Assigned |  |  |  |  | Task finished
T06.02 | Check if there was a death | pp | Assigned |  |  |  |  | Task finished
T06.03 | Store death date | pp | Assigned |  |  |  |  | Task finished
T06.04 | Store divorce date | pp | Assigned |  |  |  |  | Task finished
T06.05 | Compare divorce date and death date | pp | Assigned |  |  |  |  | Task finished
US07 | Less then 150 years old | su | Assigned | 9 | 180 | 34 | 60 | Completed
T07.01 | Check if there was a death | su | Assigned |  |  |  |  | Task finished
T07.02 | If death, store death date | su | Assigned |  |  |  |  | Task finished
T07.03 | If no death, store today's date | su | Assigned |  |  |  |  | Task finished
T07.04 | Store birth date | su | Assigned |  |  |  |  | Task finished
T07.05 | Calculate age | su | Assigned |  |  |  |  | Task finished
T07.06 | Compare to 150 years old | su | Assigned |  |  |  |  | Task finished
US08 | Birth before marriage of parents | su | Assigned | 3 | 60 | 44 | 90 | Completed
T08.01 | Store marriage date | su | Assigned |  |  |  |  | Task finished
T08.02 | Store birth date | su | Assigned |  |  |  |  | Task finished
T08.03 | Compare birth date and marriage date | su | Assigned |  |  |  |  | Task finished
US09 | Birth before death of parents | zg | Assigned | 4 | 80 | 37 | 45 | Completed
T09.01 | Store death date of parent 1 | zg | Assigned |  |  |  |  | Task finished
T09.02 | Store death date of parent 2 | zg | Assigned |  |  |  |  | Task finished
T09.03 | Store birth date | zg | Assigned |  |  |  |  | Task finished
T09.04 | Compare death dates and birth date | zg | Assigned |  |  |  |  | Task finished
US10 | Marriage after 14 | zg | Assigned | 12 | 240 | 27 | 60 | Completed
T10.01 | Check for marriage | zg | Assigned |  |  |  |  | Task finished
T10.02 | Store marriage date | zg | Assigned |  |  |  |  | Task finished
T10.03 | Store birth date | zg | Assigned |  |  |  |  | Task finished
T10.04 | Calculate age at marriage | zg | Assigned |  |  |  |  | Task finished
T10.05 | Compare to 14 years old | zg | Assigned |  |  |  |  | Task finished
TOTAL |  |  |  | 62 | 1240 | 399 | 690
Review Results
| Keep doing: | 1. Pair/team programming
2. Modularized approach
3. Strong collaboration and teamwork
| Avoid: | 1. Avoid branches to avoid merging conflicts
2. Avoid having individual format preferences

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US11 | No bigamy | ak | Assigned | 60 | 90 | 34 | 90 | Completed
T11.01 | Check Spouse ID | [6 empty] | Task Finished
T11.02 | Find if a wife or husband has 2 spouses at the same time | [6 empty] | Task Finished
US12 | Parents not too old | ak | Assigned | 80 | 120 | 33 | 90 | Completed
T12.01 | Find Parents | [6 empty] | Task Finished
T12.02 | Find Parents age | [6 empty] | Task Finished
T12.03 | Find father age if it greater than child by 80 | [6 empty] | Task Finished
T12.04 | Find mother age if it greater than child by 60 | [6 empty] | Task Finished
US13 | Siblings spacing | el | Assigned | 50 | 90 | 42 | 90 | Completed
T13.01 | Find sibilings | [6 empty] | Task Finished
T13.02 | Find siblings age | [6 empty] | Task Finished
T13.03 | Find difference in age is greater than 8 months or less than 2 days | [6 empty] | Task Finished
US14 | Multiple births <= 5 | el | Assigned | 70 | 120 | 37 | 90 | Completed
T14.01 | Find sibilings | [6 empty] | Task Finished
T14.02 | Find no of siblings greater than equal to 5 | [6 empty] | Task Finished
T14.03 | Find siblings age is same day | [6 empty] | Task Finished
US15 | Fewer than 15 siblings | pp | Assigned | 90 | 90 | 35 | 90 | Completed
T15.01 | Find sibilings in a family | [6 empty] | Task Finished
T15.02 | Find no of siblings greater than equal to 15 | [6 empty] | Task Finished
US16 | Male last names | pp | Assigned | 75 | 90 | 35 | 90 | Completed
T16.01 | Find individuals in a family | [6 empty] | Task Finished
T16.02 | Find individuals gender | [6 empty] | Task Finished
T16.03 | Find individuals last name | [6 empty] | Task Finished
US17 | No marriages to descendants | su | Assigned | 40 | 90 | 50 | 90 | Completed
T17.01 | Iterate through families | su | Assigned |  |  |  |  | Task finished
T17.02 | Find all the children in a family | su | Assigned |  |  |  |  | Task finished
T17.03 | For each child check if the husband's ID is matching with any family members | su | Assigned |  |  |  |  | Task finished
T17.03.1 | Output the error for descendants marriage | su | Assigned |  |  |  |  | Task finished
T17.04 | For each child check if the wife's ID is matching with any family members | su | Assigned |  |  |  |  | Task finished
T17.04.1 | Output the error for descendants marriage | su | Assigned |  |  |  |  | Task finished
US18 | Siblings should not marry | su | Assigned | 40 | 90 | 69 | 120 | Completed
T18.01 | Iterate through families | su | Assigned |  |  |  |  | Task finished
T18.02 | Find all the children in a family | su | Assigned |  |  |  |  | Task finished
T18.03 | For each child check if the child is married and fetch the spouse ID, | su | Assigned |  |  |  |  | Task finished
T18.04 | Compare if a child's Spouse ID is matching with any of children in a family. | su | Assigned |  |  |  |  | Task finished
T18.04.1 | Output the error for siblings marriage | su | Assigned |  |  |  |  | Task finished
US19 | First cousins should not marry | zg | Assigned
T19.01 | Iterate through families | zg | Assigned | 65 | 90 | 49 | 60 | Completed
T19.02 | Find if there was a marriage | zg | Assigned |  |  |  |  | Task finished
T19.03 | Store husband ID | zg | Assigned |  |  |  |  | Task finished
T19.04 | Store wife ID | zg | Assigned |  |  |  |  | Task finished
T19.05 | Find family ID of husband through child | zg | Assigned |  |  |  |  | Task finished
T19.06 | Find family ID of wife through child | zg | Assigned |  |  |  |  | Task finished
T19.07 | Find husband's father | zg | Assigned |  |  |  |  | Task finished
T19.08 | Find husband's mother | zg | Assigned |  |  |  |  | Task finished
T19.09 | Find wife's father | zg | Assigned |  |  |  |  | Task finished
T19.10 | Find wife's mother | zg | Assigned |  |  |  |  | Task finished
T19.11 | Find family ID of husband's father through child | zg | Assigned |  |  |  |  | Task finished
T19.12 | Find family ID of husband's mother through child | zg | Assigned |  |  |  |  | Task finished
T19.13 | Find family ID of wife's father through child | zg | Assigned |  |  |  |  | Task finished
T19.14 | Find family ID of wife's mother through child | zg | Assigned |  |  |  |  | Task finished
T19.15 | Find if family IDs of either parent of husband and wife are the same | zg | Assigned |  |  |  |  | Task finished
T19.16 | Output an error if there is an overlap | zg | Assigned |  |  |  |  | Task finished
US20 | Aunts and uncles | zg | Assigned | 50 | 80 | 55 | 60 | Completed
T20.01 | Iterate through family | zg | Assigned |  |  |  |  | Task finished
T20.02 | Check for marriage | zg | Assigned |  |  |  |  | Task finished
T20.03 | Store husband ID | zg | Assigned |  |  |  |  | Task finished
T20.04 | Store wife ID | zg | Assigned |  |  |  |  | Task finished
T20.05 | Find family ID of husband through child | zg | Assigned |  |  |  |  | Task finished
T20.06 | Find family ID of wife through child | zg | Assigned |  |  |  |  | Task finished
T20.07 | Find siblings of husband | zg | Assigned |  |  |  |  | Task finished
T20.08 | Find siblings of wife | zg | Assigned |  |  |  |  | Task finished
T20.09 | Find children of each sibling | zg | Assigned |  |  |  |  | Task finished
T20.10 | Check if husband ID or wife ID is in children of each sibling | zg | Assigned |  |  |  |  | Task finished
TOTAL |  |  |  | 430 | 650 | 330 | 600
Review Results
| Keep doing: | 1: Constant communication with all team members
2: One single branch
3: keep a modular approach
| Avoid: | 1: coding before pulling from github
2: keeping meeting off until the last minute

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US21 | Correct gender for role | ak | Assigned | 20 | 30 |  |  | Not Started
T21.01 | Check gender with Husb or Wife
US22 | Unique IDs | ak | Assigned | 20 | 30 |  |  | Not Started
T22.01 | Store all ID's
T22.02 | Check if all are unique, and return boolean
US23 | Unique name and birth date | el | Assigned | 30 | 90 |  |  | Not Started
T23.01 | Store all name and dates
T23.02 | Check if all are unique, and return boolean
US24 | Unique families by spouses | el | Assigned | 30 | 90 |  |  | Not Started
T24.01 | Find all spouses in each family
T24.02 | Check if all are unique, and return boolean
US25 | Unique first names in families | pp | Assigned | 40 | 60 |  |  | Not Started
T25.01 | Find all families and grab first names
T25.02 | Check if all are unique, and return boolean
US26 | Corresponding entries | pp | Assigned | 40 | 60 |  |  | Not Started
T26.01 | Grab all id's
T26.02 | Check that none have empty attributes
US27 | Include individual ages | su | Assigned | 25 | 60 |  |  | Not Started
T27.01 | Grab all individuals
T27.02 | Find their own age
US28 | Order siblings by age | su | Assigned | 20 | 60 |  |  | Not Started
T28.01 | Find all siblings
T28.02 | Sort them by age
US29 | List deceased | zg | Assigned | 25 | 30 |  |  | Not Started
T29.01 | Find all individuals
T29.02 | Check if they died
US30 | List living married | zg | Assigned | 30 | 30 |  |  | Not Started
T30.01 | Find all married couples
T30.02 | Check if they are living

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Stories
Story ID | Story Name | Story Description
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date
US02 | Birth before marriage | Birth should occur before marriage of an individual
US03 | Birth before death | Birth should occur before death of an individual
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage
US05 | Marriage before death | Marriage should occur before death of either spouse
US06 | Divorce before death | Divorce can only occur before death of both spouses
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people
US08 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce)
US09 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old)
US11 | No bigamy | Marriage should not occur during marriage to another spouse
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US14 | Multiple births <= 5 | No more than five siblings should be born at the same time
US15 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family
US16 | Male last names | All male members of a family should have the same last name
US17 | No marriages to descendants | Parents should not marry any of their descendants
US18 | Siblings should not marry | Siblings should not marry one another
US19 | First cousins should not marry | First cousins should not marry one another
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews
US21 | Correct gender for role | Husband in family should be male and wife in family should be female
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file
US24 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent.
US27 | Include individual ages | Include person's current age when listing individuals
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first
US29 | List deceased | List all deceased individuals in a GEDCOM file
US30 | List living married | List all living married people in a GEDCOM file
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file
US32 | List multiple births | List all multiple births in a GEDCOM file
US33 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file
US34 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse
US35 | List recent births | List all people in a GEDCOM file who were born in the last 30 days
US36 | List recent deaths | List all people in a GEDCOM file who died in the last 30 days
US37 | List recent survivors | List all living spouses and descendants of people in a GEDCOM file who died in the last 30 days
US38 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days
US39 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days
US40 | Include input line numbers | List line numbers from GEDCOM source file when reporting errors
US41 | Include partial dates | Accept and use dates without days or without days and months
US42 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate)